## Slide 1: MOMA – MoNTESSORI Method for Orienting and Motivating Adults
Project n. 527800-LLP-1-2012-1-IT-GRUNDTVIG-GMP)
Technical College of Transports and Constructions Iasi
Romania
NATIONAL dissemination progress report
December 11-12, 2013

## Slide 2: 1. LOGO - The visual impact - Creating distinctive graphic symbol
9 proposals on the platform
all partners voted the final version on 1 June, 1, 2013 (Evora meeting)
IMPACT
visual identity trying to express the spirit of the Project - recognition the project and the message sent “adults in difficulty, need special educational alternative” > together we can …reusi

## Slide 3: 2. Interviews with experts
Elena Matei General Directorate for Assistance and Protection of Adults - Adult Residential Center
http://www.youtube.com/watch?v=DSwXEBdyhJk&feature=youtu.be
Marius Vulpe, Director at Iasi Penitenciary
http://www.youtube.com/watch?v=95k1nqpNTbQ&feature=youtu.be

## Slide 4: 3. NEWSLETTER
3 newsletter in EN and 2 in RO were posted on the project platform:
- first newsletter > what means Montessori method and why we wanted to
implement at adults level ( general information, ideas,
- second newsletter > 14 interviews filmed, with experts from all the
countries involved (let’s talk about ‘absorbing mind’)
- third newsletter > aspects from national research ( ‘social research’)
IMPACT
Articles were/will be published in local/national newspapers in the native language, to stimulate the people interes, for this type of alternative education, for adults in needs

## Slide 5: the newsletters have been distributed :
February, 10 2013 – ANFPCDEFP - National Agency for Community Programs for Education and Professional - Florentina Anghel – responsible Development.
- Article “Adult Education in Romania” on yahoo grundtvigers
groups.yahoo.com/group/grundtvigers/message/5333‎
July, 24 2013 - Ziarul de Iasi - http://www.ziaruldeiasi.ro/invatamant/85-000-de-euro-pentru-trei-licee-din-iasi-care-deruleaza-un-parteneriat-pentru-invatare~ni8o2c
November,21 2013 - County School Inspectorate of Iasi
- The first newsletter was posted on the proiecte.isjiasi@yahoo.com
MOMA project popularization and stimulating teachers and schools for their involvement in the development and future European activities

## Slide 6: 5. EUROPEAN BROCHURE
28 brochures were made in EN language with ‘social research” developed in all the countries involved :
- 7 brochures for National Library to obtain ISBN – December, 6, 2013
- 8 brochure for the project partners
- 5 brochures for Technical College of Transports and Constructions, Iasi
- 2 brochures for County School Inspectorate Iasi
- 2 brochures for stake holders (experts)
IMPACT - Informing the authorities and different institutions about the educational alternative, for adults in needs to change their life. Improving the lives of adults, distressed, and sustainable growth in the number of adults from disadvantaged groups, which are integrated into society on the basis of personal competence and socio-professional. The possibility of including Montessori teaching method approach to adults in national curriculum
4. national BROCHURE
IMPACT - Innovative educational approaches and methods to learning and teaching the social competences: the link between the lack of social competences and the participation of the socially vulnerable target-groups to the lifelong learning programs -50 books in RO and EN language with ISBN 978-606-624-446-6
- 7 brochures for National Library to obtain ISBN – December, 6, 2013
- 2 brochure for Teacher Training Centre
- 10 brochures for Technical College of Transports and Constructions, Iasi
- 6 brochures for County School Inspectorate Iasi
- 4 brochures for stake holders (experts

## Slide 7: 6. VIDEODOSSIER STEP BY STEP
- 3 video dossiers ( May 22, May 25, June 19 2013) presented in school, partner institution, School Inspectorate, Teacher Training Centre ,in the Workshop Project living/ A paradigm, two training systems: Anglo Saxon and Romanian
IT IS NECESSARY TO RECEIVE FROM ALL PARTNERS SHORT FILMS, PHOTOS, FLYERS , OTHER IMPACT DOCUMENTS
IMPACT
The video has made ​​it a commitment to long-term, able to ensure stability and improving the quality of the educational targets and integrate the results of the current experiment in alternative teaching strategies, capacity development approach that seeks adult in difficulty to integrate social

## Slide 8: 7. the websites where the project website has been diffused
project presentation in prezi : 17.12.2012
http://prezi.com/mifjy-wql6ts/montesori-project/
project presentation on the site of School inspectorate - 27 .01.2013
www.proiecte.isjiasi@yahoo.com
Interview Matei Elena – expert MOMA - 12.11.2013
http://www.youtube.com/watch?v=DSwXEBdyhJk&feature=youtu.be
Interview Marius Vulpe – expert MOMA - 12.11.2013
http://www.youtube.com/watch?v=95k1nqpNTbQ&feature=youtu.be
Article published in the “ Ziarul de Iasi” newspaper - - 24.07.2013
http://www.ziaruldeiasi.ro/invatamant/85-000-de-euro-pentru-trei-licee-din-iasi-care-deruleaza-un-parteneriat-pentru-invatare~ni8o2c

## Slide 9: 8. ACTIVITIES
1. Meeting for the partnership / collaboration protocols with different institutions, corresponding to the target group of the project (05.03.2013, 05.03.2013, 17.03.2013, 15.11.2013) at Technical College of Transports, Iasi – RO, Penitentiary of Iasi and General Directorate for Assistance and Protection of Adults - Adult Residential Center
Description of the activity
Maintaining and developing the collaboration with institutions involved (stake holders)
  Iasi Penitentiary (director + 3 persons)
  41 School of Iasi Penitentiary(director + 2 persons)
  General Directorate for Assistance and Protection of Adults - Adult Residential Center(3 persons)
  County Agency for Employment, Iasi AJOFM(director + 1 person)
  Foundation "Equal opportunities for women (director)
  Teacher’s Training Centre of Iasi (partner) ((director + 1 person)
  Protocol signed with stake holders

## Slide 10
2. Teacher’s Council - April, 18 2014 - Technical College of Transports, Iasi – RO – Mediatech
Description of the activity
In the Teachers' Council, was presented MOMA project with all mobilities , the activities of the team of professors and experts the stakeholders involved. All materials were translated and we prepared the detail’s for interviews
Participants - 22 teachers; Evidences - Meeting minutes.
3. Workshop Project living/ A paradigm, two training systems: Anglo Saxon and Romanian - May, 29-30, 2013 - Teacher’s Training Center
Description of the activity
The Teachers Training Centre organized a workshop and a round table discussion and presentations - live workshop projects at the Conference - a paradigm, two training systems: Anglo-Saxon and Romanian.
29 participants
Evidences: Video dossier step by step, Application form for the presentation of the project, Program/ Agenda, Diploma, Meeting minutes – table with signatures, photo

## Slide 11
4. Teacher’s Council - October,10 2013 - Technical College of
Transports, Iasi – RO (Amphitheatre)
Description of the activity
Analysis of annual educational process with the European dimension. Presentation the MOMA project : video dossier, brochure with research in RO, EN, first newsletter
Participants - 33 teachers; Evidences - Meeting minutes
5. National Conference - September, 26 2013 - Teacher’s Training Center
Description of the activity
Involving schools, authorities in promoting educational alternative in the long term / permanent adult and experimental knowledge MOMA; Presenting our research and dissemination activities
Participants - 41 participants
Evidences - Distributions the brochures /books and video dossiers, meeting minute